## Global Planning Sheet
| Nils Meijer - 466301 | Global Planning
Describe in short the skill(s) you intend to aquire: |  | Describe in short the product which will prove your skills (deliverable): |  |  | 2023-02-14
↓ Phases ↓ | What are you going to do? | What do you need for it? Tasks, people, knowledge, skills, … | What are you going to deliver? | Week |  | 1 ECTS = 28 hours of study load. This minor is 30 ECTS
Watch out: the phases don't necesserily represent the weeks between the assessment.If you finish one phase, you can move on to the next one. |  |  |  | (18 weeks* total, 40 hours per week) |  | The final presentation will take place in either week 19 or 20 (2.9 or 2.10)
1. Discover | Brainstorm possible product concepts | Inspiritation from several sources (existing games, prototype demos on youtube), an estimation of what I can do in 5 months | A document (mindmap, list with ideas, for example.) containing several ideas with possible features that are related to the skills I want to learn | 1
| Research the technologies/algorithms I need to learn about to make the mentioned ideas in the brainstorm document | Youtube tutorials, ebooks, GDC talks. | A document with the technologies/algorithms I have found | 1
| Research existing implementations of mentioned concepts & features | Steam pages, promotional content, gameplay videos | A document (moodboard?) of the games/implementations I have found | 1
2.Define | Plan/design MVP mechanics | A rough idea about the final product. | A design document describing the mechanics for the concept I have chosen | 1
| Make planning/estimated hour registration for mechanics. Rank importance for MVP. Highest priority first | An estimation of time for each feature. | Planning sheet containing the features the MVP should have, with an estimated hour count | 1
3. Develop
4. Deliver
* End presentation might take place as soon as week 19

## Global Planning Sheet Example
| Your name and student number | Global Planning
Describe in short the skill(s) you intend to aquire: |  | Describe in short the product which will prove your skills (deliverable): |  |  | 2023-02-14
↓ Phases ↓ | What are you going to do? | What do you need for it? Tasks, people, knowledge, skills, … | What are you going to deliver? | Week |  | 1 ECTS = 28 hours of study load. This minor is 30 ECTS
Watch out: the phases don't necesserily represent the weeks between the assessment.If you finish one phase, you can move on to the next one. |  |  |  | (18 weeks* total, 40 hours per week) |  | The final presentation will take place in either week 19 or 20 (2.9 or 2.10)
1. Discover | Research various f2p games and compare what they have in common | Knowledge of most successful f2p games | Document with overview of the games and a comparison table | 1
| Research strategy games find out what mechanics are prefered by players | Figure out what target audience I want to approach with my game | Document with overview of the games and a comparison table | 2
| Target audience research and analysis | Some tool for target audience analysis | Target audience definition and personas | 3
| Research on monetization models and strategies | Preferably help from an industry expert | Overview of monetization models and strategys and how I can apply it to my game | 4
2.Define | Design game mechanics | Input from game design teacher. For instance Max. | Game design first draft | 5
| Design UX/UI | Input from UX/UI teacher. For instance Alejandro. | Game design final document | 6
| Establish a workflow for the production | Confirmation from other designers, artists and programmers (maybe from fellow Students) | Workflow / planning document. Asset list, | 7
3. Develop | Produce concept art | Help from concept artist | Finished concept art so I can use if for 3d modeling and level design | 8
| Produce 3d assets | More 3d artists | 3d assets from asset list | 9
| Programming prototype | Knowledge of C# within Unity and/or support from a programmer | Playable prototype | 10, 11
| Learning C# | Support from a programmer | Playable prototype | 12
| Programming the game and implementing all assets | More time | Beta version of my game | 13, 14
| Ballancing gameplay | Loads of people for playtesting | Ballanced and tested gameplay | 15, 16
4. Deliver | Last bit of polishing gameplay / art / and sound (oh no you forgot about that) | Help from an sound expert like e.g. Mr. Hulzebosch. | Finished, polished game | 17
| Writing documentation and preparing presentation | Feedback from my fellow students | Written report and a powerpoint presentation | 18
| Presenting my final game at school and at the GDC to some potential investors | Help from (the)GOD(s) | The best elevator pitch in the history of mankind | 19
* End presentation might take place as soon as week 19